## v1.2
Phase | Section (Title) | Section Link | Date | Bitácora Entry (Literal Description) | Technical Detail / Business Impact | Estimated Impact | Status | Key Milestone
Phase 1 | Karbon Cleanup: Big Data Analysis |  | Aug - Sep 5 | Analysis of the total universe of 16,742 entities migrated from Office Tools. Identification of duplicate, inactive, and obsolete records. | Legacy Data Quality Diagnosis: Identifying 82% "noise" in the original database to prevent systemic inefficiency and data corruption. | Data Efficiency | Done | No
Phase 1 | Karbon Cleanup: Strategic Validation |  | Aug - Sep 5 | Work sessions with Christian (Co-Owner) to validate doubtful records and define CRM retention criteria. | Data Governance: Expert-level filtering to ensure the database only contains clients with current commercial relevance for the firm. | Data Integrity | Done | No
Phase 1 | Karbon Cleanup: Final Execution |  | Finished Sep 5 | Systematic deletion of unvalidated records, consolidating a clean database of 3,018 active clients. | CRM Sanitation: Established a solid and reliable foundation for all subsequent automation phases and the CRM lifecycle. | Systems Integrity | Done | Yes
Phase 1 | Unique ID: Structure Definition |  | Sep 08 | Design of the unique identification logic: combination of Client Initial + 3-digit Numeric Sequence (e.g., M001). | Identity Architecture: Creation of a universal primary key to prevent duplication and facilitate high-speed cross-platform search. | Systems Integrity | Done | Yes
Phase 1 | Unique ID: Conflict Resolution |  | Sep 8 - Oct 10 | Technical resolution of conflicts due to identical names (e.g., Rodriguez, John vs. Rodriguez, John M) using the Unique ID system. | Expert Risk Mitigation: Elimination of cross-assignment risks for documents or invoices between namesake clients. | Risk Mitigation | Done | No
Phase 1 | Unique ID: Platform Mapping |  | Sep 8 - Oct 10 | Execution of mapping and linking of Unique IDs between Karbon and Square to ensure data parity. | Interoperability: Ensuring financial records in Square match operational and tax records in Karbon without error. | Automation | Done | No
Phase 1 | Karbon Enrichment Phase |  | Oct 13 - Nov 1 | Massive profile enrichment phase for the 3,018 clients: verified entry of emails, phone numbers, and physical addresses. | Data Quality: Drastic improvement in reachability and prepared the system for the Client Portal deployment. | Data Quality | Done | No
Phase 1 | IRIS: Credential Validation |  | Oct 16 - 18 | Review and confirmation of the Transmitter Control Code (TCC) processed in Nov 2024 (Ref: p5903 IRIS TCC.pdf). | Compliance Validation: Expert confirmation of the firm's legal authorization to transmit data directly to the IRS. | Legal Compliance | Done | No
Phase 1 | IRIS: Requirements Engineering |  | Oct 16 - 18 | Technical study of Publication 5717 (IRIS User Guide) to determine required data structures for bulk uploads. | Technical Analysis: Decoding complex government data schemas to design automated bulk upload scripts. | Legal Compliance | Done | No
Phase 1 | Square: Catalog Audit |  | Oct 16 | Extraction and audit of the original Square catalog (file: catalog_data_full.xlsx with 211 items). | Product Diagnosis: Identification of inconsistencies in service nomenclature and non-standardized pricing hierarchies. | Catalog Quality | Done | No
Phase 1 | Square: Restructuring Proposal |  | Oct 16 - 24 | Development of the detailed report (proposed_catalog_restructuring.xlsx) with new base names, variations, and modifiers. | Catalog Engineering: Designing a logical sales structure to facilitate service selection and accurate revenue reporting. | Catalog Quality | Done | No
Phase 1 | Payroll: Historical Extraction |  | Oct 20 | Extraction of 2024 legacy data from 1099ETC software; generated compressed archive 1099etc.w24.zip. | Data Sovereignty: Recovery of historical records for transformation into modern, processable digital formats. | Data Migration | Done | No
Phase 1 | Payroll: Data Normalization |  | Oct 22 | Generation of Payers.xlsx (Unique Payers) and EFD_data.xlsx (828 recipient/recipient records). | Expert Data Engineering: Transforming raw legacy data into normalized structures for automated bulk submission. | Automation | Done | Yes
Phase 1 | Karbon: C-Groups Implementation |  | Oct 24 - 27 | Configuration of the "C-Groups" architecture to hierarchically link Corporations with their respective Owners. | 360° Visibility: Drastic improvement in client management by allowing a consolidated view of familial and business groups. | 360 Visibility | Done | Yes
Phase 1 | IRIS: Technical Enablement |  | Oct 24 - 27 | Review of training material (iris-101.pdf) and IRS 1099-NEC template format guidelines. | Specialized Training: Technical preparation for using the IRS's official transmission platform and bulk protocols. | QA / Validation | Done | No
Phase 1 | Square: Pricing Engineering |  | Oct 24 | Configuration of "Item Options" and correction of ordinal error: Surcharge set as Ordinal 0 (Default). | Revenue Optimization: Ensuring full price capture by default, preventing accidental or unauthorized discounts. | Revenue Optimization | Done | Yes
Phase 1 | Square: Sandbox Deployment |  | Oct 24 | Deployment of the optimized catalog under the "TEST IT - NEW ITEMS" category in the Square production environment. | Real-Environment QA: Validation of the functional sales model without impacting live daily business operations. | QA / Validation | Done | No
Phase 1 | Square: Submission to Management |  | Oct 24 | Formal submission of the restructuring report and sandbox catalog access to Nathalie for leadership approval. | Corporate Governance: Strategic alignment between technical architecture and senior management requirements. | Stage Closure | Done | No
Phase 1 | EFTPS: Security Configuration |  | Oct 16 - 24 | Activation of the EFTPS Batch Provider and security protocol audit for federal tax payments. | Financial Cybersecurity: Establishing a secure and centralized channel for professional federal tax management. | Financial Security | Done | No
Phase 1 | IRIS: Template Engineering |  | Oct 24 - 27 | Design of custom CSV templates based on IRS technical requirements for massive submission. | Asset Development: Creation of the technical data bridge that eliminates the need for manual record entry. | Automation | Done | No
Phase 1 | IRIS: Process Certification |  | Oct 27 | Successful pilot upload of 10 1099-NEC records to validate IRS acceptance flow and system timing. | Product Validation: Final proof of concept ensuring 100% process success for high-volume filing season. | QA / Validation | Done | No
Phase 1 | Strategic Audit & Configuration (Karbon) |  | Nov 27 - 28 | NY Trip to visit JW office. | Expert Technical Audit: On-site audit and workflow diagnosis at the main office to establish baseline operational requirements. | Strategic Validation | Done | No
Phase 1 | Strategic Audit & Configuration (Karbon) |  | Dec 1 - 5 | Configure and add all Karbon works for the Bookkeeping department with the suggested strategies: one work per year with periodic tasks according to the service. | Workflow Engineering: Implementation of a structured recurring task system to optimize annual project visibility and tracking. | Management Efficiency | Done | Yes
Phase 1 | Strategic Audit & Configuration (Karbon) |  | Dec 8 - 9 | Renamed ProSeries files that did not meet the suggested standard to match them with the Unique Client ID. | Data Integrity: Massive record matching to ensure system parity and eliminate identity conflicts in fiscal software. | Data Integrity | Done | No
Phase 1 | Strategic Audit & Configuration (Karbon) |  | Dec 12 - 13 | Return trip to Pereira. | Conclusion of the first on-site immersion and technical diagnosis phase at the New York headquarters. | Stage Closure | Done | No
Phase 1 | Strategic Audit & Configuration (Square) |  | Dec 10 - 11 | Square Catalog TEST review in a short meeting with Nathalie, Diego, and Christian; took notes on suggested changes. | Quality assurance and stakeholder feedback session to refine the digital service item architecture and pricing logic. | Catalog Quality | Done | No
Phase 1 | Strategic Audit & Configuration (Square) |  | Dec 18 - 22 | Deleted TEST catalog and generated the Final Catalog with suggestions from training and meetings; sent official email to the team. | Production Deployment: Final catalog is officially Live after expert validation, executive review, and team training. | Revenue Standardization | Done | Yes
Phase 1 | Strategic Audit & Configuration (Square) |  | Dec 23 - 26 | Detected new clients in ProSeries and added them to Square to be ready for the season. | Proactive database synchronization to ensure billing and service readiness before the tax season kickoff. | Season Readiness | Done | No
Phase 1 | Team Enablement and Adoption |  | Dec 6 - 9 | Created training slides for the team about Karbon, Square, Unique ID, C-Groups, and the standardized creation of notes and works. | Knowledge Management: Developing high-level technical assets for team standardization and operational alignment. | Training Assets | Done | No
Phase 1 | Team Enablement and Adoption |  | Dec 11 | Team training on the mentions from the slides, Square management, Invoices, payments, and the new catalog with modifiers. | Expert Training: Empowering staff in the execution of new billing, pricing, and documentation protocols. | Team Adoption | Done | No
Phase 1 | Team Enablement and Adoption |  | Dec 16 - 18 | Adjusted slides to match training feedback and agreements; sent official manual document with final changes via email. | Finalizing documentation and establishing a single source of truth (SSoT) for standardized team procedures. | Documentation | Done | No
Phase 2 | Automation & RPA Development |  | Jan 5 | In a virtual meeting, received a request for the automation of a process to accept appointments generated via Square Appointments. | R&D / Feasibility Research: Rule-based automated workflow optimization analysis based on specific service types. | R&D / Innovation | Done | No
Phase 2 | Automation & RPA Development |  | Jan 5 - 10 | Feasibility tests for Square appointment acceptance via n8n and Square API; the bot detects the event but the API restricts status change. | Expert Technical Diagnosis: Identification of API limitations to define alternative Robotic Process Automation (RPA) routes. | Technical Analysis | Done | No
Phase 2 | Automation & RPA Development |  | Jan 9 - 12 | RPA development for automated acceptance of deferred appointments via browser automation and GUI (local machine tests). | Expert Workaround: Developing browser-based automation to overcome official API status-change restrictions. | RPA Solution | Done | No
Phase 2 | Infrastructure & Monitoring |  | Jan 13 - 14 | Added Telegram notifications for the bot to alert accepted appointments and confirm continuous operational status. | Telemetry Implementation: Real-time monitoring and alerting for unattended automated bot processes. | Monitoring | Done | No
Phase 2 | Infrastructure & Cloud Deployment |  | Jan 14 - 16 | Deployment of the RPA bot to Google Cloud (GCC) for 24/7 uptime during the trip without personal machine dependence. | Cloud migration to ensure high availability and resource decoupling from personal hardware for 24/7 reliability. | Cloud Stability | Done | Yes
Phase 2 | Logistics |  | Jan 19 - 20 | Preparations for the second trip to NY. | Logistical and technical readiness for the second on-site season support and intervention mission. | Readiness | Done | No
Phase 2 | Logistics |  | Jan 21 - 22 | Trip to NY to provide on-site support to the team during the peak tax season. | Critical technical assistance and expert supervision during high-volume seasonal operations at the office. | Business Continuity | Done | No
Phase 2 | MEGA Revenue Tracker |  | Jan 22 - 24 | Updated Square app for API; closure is faster, downloads partial payments, splits tips to account 13, and loads refunds. | Advanced Financial Engineering: Automating the split of tips and reconciliation of partial/refunded payments via API. | Financial Efficiency | Done | Yes
Phase 2 | MEGA Revenue Tracker |  | Jan 23 - 24 | Updated interface colors and logos with the new branding. | UI/UX alignment of internal proprietary tools with the firm's refreshed corporate identity. | Branding | Done | No
Phase 2 | MEGA Revenue Tracker |  | Jan 26 | Update to recognize Zelle payments with common typos (e.g., zel, zell). | Fuzzy Logic Implementation: Minimizing manual record correction and improving payment attribution accuracy. | Error Reduction | Done | No
Phase 2 | MEGA Revenue Tracker |  | Jan 26 - 28 | Added editable table to the Square Up API module for manual validation before final database submission. | Implementing a "Human-in-the-loop" validation layer to ensure transactional data integrity before database persistence. | Quality Control | Done | No
Phase 2 | MEGA Revenue Tracker |  | Jan 27 - 28 | In Admin, added summary of payment methods, totals, and print functions. | Business Intelligence: Dashboard development for executive oversight and real-time financial auditing of sales. | BI Dashboard | Done | No
Phase 2 | MEGA Revenue Tracker |  | Jan 30 - Feb 3 | Adjusted API transaction window (UTC to NY -5 UTC) to fix late-night inconsistencies; tested with Nathalie. | Timezone Synchronization: Resolving discrepancies to ensure 100% precision in reporting for nocturnal transactions. | Data Integrity | Done | No
Phase 2 | MEGA Revenue Tracker |  | Feb 4 - 5 | Interface change for NoAdmin users: removed "New Record" and added "Dashboard" for personal metrics. | Process Enforcement: Redirecting data entry exclusively to Square as the primary Single Source of Truth (SSoT). | Process Control | Done | No
Phase 2 | MEGA Revenue Tracker |  | Feb 05 | Login patch for Lex Urrea account name conflict (Google: Taxes JW vs Square: Lex Urrea). | Identity Resolution: Ensuring correct sales and record attribution for users with disparate credentials. | Identity Support | Done | No
Phase 2 | AI & Advanced Tools |  | Jan 23 | Created custom Gemini GEM with Diego for internal firm consultancy. | Expert AI Engineering: Developing proprietary agents to streamline technical drafting and specialized firm consultancy. | AI Innovation | Done | No
Phase 2 | Tax Season Tools (PDF Splitter) |  | Jan 20 - 23 | Development of Splitter PDF module for 1099 forms. | Automation Engineering: Large-scale document segmentation to optimize the tax season workflow. | Time Saving | Done | No
Phase 2 | Tax Season Tools (PDF Splitter) |  | Jan 24 - 27 | Development of Splitter PDF module for W2 forms (Accountants World). | Engineering automated document processing for high-volume payroll distributions. | Automation | Done | No
Phase 2 | Tax Season Tools (PDF Splitter) |  | Jan 24 - 27 | Development of Splitter PDF module for W2 forms (ADP). | Implementing multi-platform support for ADP payroll document segmentation via automation scripts. | Automation | Done | No
Phase 2 | Tax Season Tools (PDF Splitter) |  | Jan 25 - Feb 3 | Development of Splitter PDF module for K1 forms. | Specialized Automation: Segmenting K1 shareholder and corporate tax documents for mass distribution. | Automation | Done | No
Phase 2 | Tax Season Tools (PDF Splitter) |  | Jan 30 - Feb 2 | Development of Splitter PDF module for Paystubs (Accountants World). | Streamlining document delivery workflows for the payroll department via automated segmentation. | Efficiency | Done | No
Phase 2 | Strategic Consulting (Karbon) |  | Jan 24 | Silvia no tiene permisos de Merge en Karbon: Nathalie me explica que mejor no le demos los permisos. | Data Governance Expert Intervention: Denied irreversible permissions to mitigate high risks of data loss at frontdesk. | Risk Mitigation | Done | No
Phase 2 | Hardware & Infrastructure |  | Jan 23 | Installed Python on the new office PC for bot execution. | Provisioning local compute resources for high-performance Python-based automation tasks. | Infrastructure | Done | No
Phase 2 | Hardware & Infrastructure |  | Jan 23 | Installed VS Code on the new office PC for bot maintenance. | Establishing on-site development tools for rapid incident response and script management. | Infrastructure | Done | No
Phase 2 | Hardware & Infrastructure |  | Jan 24 - 26 | Installed ProSeries on the new office PC for bots. | Integrating core tax software into the local automated processing server environment. | Infrastructure | Done | No
Phase 2 | Hardware & Infrastructure |  | Jan 28 | Coordinated Firewall activation for remote bot access with Computero. | Cybersecurity Engineering: Securing local infrastructure for remote management and monitoring. | Cybersecurity | Done | No
Phase 2 | Strategic Audit (Karbon) |  | Jan 23 - 24 | Investigated Karbon Works marked as done without files (identified Mobile UX/button visibility issue). | UX Audit: Identification of interface limitations on mobile devices and creation of education protocols for clients. | Support Quality | Done | No
Phase 2 | Incident Management |  | Jan 27 - 28 | Reported Karbon file visualization error and opened ticket 00151759. | SaaS Vendor Management: Escalating critical bugs to ensure operational service continuity. | Vendor Mgmt | Done | No
Phase 2 | Compliance & Filing |  | Jan 29 | Submitted 13 1099 extensions via the IRIS platform. | Ensuring regulatory tax compliance for clients during peak operational season. | Compliance | Done | No
Phase 2 | Strategic Audit (Square) |  | Jan 30 | Escalated Square Dashboard card-adding limitation on PC; proposed mobile alternative. | Troubleshooting platform-specific functionality gaps and providing operational workarounds. | Problem Solving | Done | No
Phase 2 | Compliance & Filing |  | Jan 28 - Feb 3 | CSV standardization for IRIS 1099-NEC (Silver Tray case); pending client payment confirmation. | Expert Data Engineering: Formatting complex CSV structures for massive contractor reporting requirements. | Data Prep | Done | No
Phase 2 | AI Training & Mentoring |  | Jan 30 - 31 | Advanced Gemini training for Nataly Castro including Canvas, doc uploads, and professional redacting. | Upskilling team leadership in advanced generative AI usage for technical and professional drafting. | Talent Training | Done | No
Phase 2 | Data Integrity & Backups |  | Jan 29 - 30 | Transferred ProSeries backups (2023-2024) to a shared Google Drive disk. | Implementing data redundancy and disaster recovery protocols for historical tax records. | Backup | Done | No
Phase 2 | Branding |  | Jan 30 | Attended professional photography session for the firm's web portal. | Coordinating professional brand updates and professional image alignment for digital platforms. | Visual Identity | Done | No
Phase 2 | Strategic High-Level Consulting |  | Feb 2 | Engineered the Final Version of the Deleon Creative LLC Contract incorporating an AI-Shielded Response Strategy. Detected that external contract modifications were being autonomously generated by third-party AI; developed a counter-strategy to neutralize non-expert algorithmic suggestions. Provided CEO Diego with the final instrument and the precise technical framework for contractual drafting. | Adversarial AI Mitigation: Protecting firm interests by identifying and neutralizing hallucinated or suboptimal AI-generated legal clauses. Established a "Shielded Response" protocol to maintain human-expert governance over automated interference. | Contract Shield | Done | Yes
Phase 2 | Strategic High-Level Consulting |  | Feb 3 | Performed final forensic audit of the DeLeon contract. Identified critical date inconsistencies and validated salary evolution parameters. Addressed a high-risk structural conflict regarding Florida Labor Law (Dual Employee/Employer status for Ana). Strategically withheld a new redacted document to prevent recursive AI friction, delivering instead a final expert resolution. Case closed to full client satisfaction. | Legal-Technical Compliance: Resolved complex employment status paradoxes under Florida jurisdiction. Advanced Consulting: Utilized a "Communication-Only" strategy to bypass the client's AI feedback loop, ensuring structural integrity without triggering further automated errors. | Risk Mitigation | Done | Yes
Phase 2 | Automation Debugging |  | Feb 2 - 3 | Bot adjustment for Christian's personal tax appointments (Auto-accept logic fix). | Maintaining RPA reliability through iterative debugging of specific user permissions and edge cases. | RPA Maintenance | Done | No
Phase 2 | Compliance & Filing |  | Feb 02 | Submitted 3 additional 1099 extensions due to documentation delays. | Regulatory Catch-up: Finalizing extensions to avoid late-filing penalties for clients. | Compliance | Done | No
Phase 2 | Team Enablement (AI Training) |  | Feb 01 | LedgerBot support for Lizmarie: Training on transaction uploads, backups, and session restore. | User Enablement: Training staff on proprietary AI assistant tools to optimize internal financial processing. | User Enablement | Done | No
Phase 2 | Infrastructure |  | Feb 04 | Modified Square webhook subscription for MEGA RT after delivery failure reports. | Real-time Data Restoration: Repairing critical data streams between payment and tracking platforms. | Data Stability | Done | No
Phase 2 | Accounting Standardization |  | Feb 04 | Optimized tip registration flow and created variable item "Tips" (Non-taxable). | Financial Standardization: Ensuring accurate gratuity tracking and accounting integrity via official protocol. | Accounting Integrity | Done | No
Phase 2 | Crisis Management |  | Feb 04 | Monitored major Square global outage and managed internal communication (issquareup.com). | Crisis Leadership: Monitoring critical infrastructure downtime and managing firm-wide risk communication. | Risk Mgmt | Done | No
Phase 2 | UX Optimization |  | Feb 3 - 4 | Reordered Booking presentation using ASCII characters and bullets (bypassing alphabetical sort). | Technical UX Hack: Overcoming platform limitations to improve preparer visibility for customers via ASCII indexing. | UX Optimization | Done | No
Phase 2 | Software Compliance |  | Feb 4 - 5 | Updated 1099ETC software to the Jan 2026 version for Form 940 correction. | Critical Compliance Update: Correcting historical reporting errors (2024/2025) via specialized software updates. | Critical Update | Done | No
Phase 2 | Automation (Payroll) |  | Feb 5 - 6 | Bulk annual Work creation in Karbon via API for 153 clients; trained Erika on the process. | Hiper-automation: Using the API to scale operations and upskilling leads on new API-driven workflows. | Hiper-automation | Done | Yes
Phase 2 | Catalog Management |  | Feb 05 | Added 5 new catalog items and reinforced Tip manual protocol to the team. | Inventory Expansion: Maintaining the service catalog and enforcing strict revenue capture protocols. | Revenue Mgmt | Done | No
Phase 2 | Cloud Optimization |  | Feb 05 | RPA Cloud scaling and billing/feasibility evaluation after the Square platform update. | Resource Management: Balancing cloud compute capacity against budget constraints for bots after Square UI changes. | Cost Optimization | Done | No
Phase 2 | Data Integrity |  | Feb 04 | Eliminated "One-time items" in Square and established "Add discount" as the authorized method. | Enforcing strict fiscal structures to ensure data integrity in departmental and tax year reporting. | Fiscal Control | Done | No
Phase 2 | Personnel Management |  | Feb 10 - 11 | Technical intervention with Ronald regarding unauthorized item creation for discounts. | Operational Governance Expert Intervention: Enforcing technical protocols and protecting financial reporting accuracy. | Governance | Done | No
Phase 2 | Compliance & Filing (IRIS) |  | Feb 6 - 11 | Silver Tray 1099 submission: JSON diagnosis, table conversion, and ITIN fix with IRS support. | Expert Troubleshooting: Solving complex filing issues via JSON reverse-engineering and federal support for ITIN recipient forms. | Conflict Resolution | Done | No
Phase 2 | Team Enablement |  | Feb 11 | C-Groups training and corporate/owner linking for Nataly in Karbon. | Expert Mentoring: Teaching advanced CRM data architecture to departmental leadership. | Data Structure | Done | No
Phase 2 | Standardization & Legal |  | Feb 13 | Created "42. Payroll Penalty" Karbon template and Square billing item "Assessment Protest". | Standardizing the protest process with legal shielding and precise automated billing logic. | Loss Mitigation | Done | No
Phase 2 | Team Enablement |  | Feb 13 | Training Erika (Payroll Lead) on MEGA Revenue Tracker for Goals monitoring. | Empowering departmental leads with real-time financial tracking and goal alignment metrics. | Mgmt by Objectives | Done | No
Phase 2 | Infrastructure |  | Feb 13 | Restarted EFTPS Batch Provider and trained Diana M. for autonomous client enrollment. | Operational Decentralization: Handing over critical tax payment tools to expertly trained staff. | Autonomy | Done | No
Phase 2 | Cloud & Cost Management |  | Feb 13 | Re-architected Replit for PayrollTools using non-autoscaling dedicated VMs. | Infrastructure Cost Engineering: Redesigning deployments to eliminate billing spikes and improve resource efficiency. | Cost Efficiency | Done | No
Phase 2 | CRM Disaster Recovery & Data Integrity |  | Feb 17 - 18 | Emergency Structural Reconstruction: Recreated the comprehensive Karbon profile for COTO SOLORZANO, HUGO ERNESTO & ALVARADO ORELLANA, DIANA - 4670 following an accidental deletion. Utilized legacy Unique Client ID mapping and historical process logs to restore profile metadata. Re-established the technical link between the individual and the associated corporate entity. Manually reconstructed the specific Tax Work item and audited the workstream to identify missing documentation, providing a precise recovery roadmap for the staff to finalize the file. | Business Continuity & Crisis Management: Mitigated the impact of human error on the firm’s core CRM. By leveraging the Unique Client ID architecture, I ensured that the restored data remained consistent with the global database. This operation required high-tier attention to detail to ensure no historical tax data was lost, emphasizing that a single accidental deletion necessitates a multi-day technical recovery to guarantee service continuity. | Disaster Recovery / Integrity | Done | No
Phase 2 | Compliance |  | Feb 18 | Finalized corrections for ten 1099 forms for Silver Tray in IRIS. | Closing the Annual Cycle: Final identity validation and filing for high-volume accounts after IRS audit. | Season Closure | Done | No
Phase 2 | SMEAC Dashboard Architecture & Governance |  | Feb 19-20 | Comprehensive updates and synchronization of the SMEAC (Situation, Mission, Execution, Administration, Command) dashboard. Conducted a technical audit of current activities, project timelines, and CTO-level advancements to ensure the master data reflects real-time operational status. | Strategic Data Governance: Ensuring the integrity of the firm’s primary decision-making tool. This provides high-level transparency and system resilience by mapping technical milestones to business objectives, allowing for precise tracking of J&W Accounting’s evolution. | Operational Transparency | Done | Yes
Phase 2 | International Operations & Logistics |  | Feb 24 - 26 | International return transit from the United States to Colombia. Managed remote oversight of firm operations and maintained communication protocols during multi-day travel window to ensure zero downtime. | System Resilience: Ensuring leadership availability and operational continuity during cross-border transitions. | Infrastructure & Continuity | Done | No
Phase 2 | Tax Season Support & Compliance |  | Feb 26 | Technical assistance to the Payroll Department for the correction of three (3) 1099-NEC forms for 'Silver Tray' via the IRIS (Information Returns Intake System) platform, following the late receipt of verified and accurate data from the business owner. | Data Governance & Risk Mitigation: Executed a critical correction workflow to ensure federal compliance. Overcame delays in client data integrity by leveraging the IRIS portal to prevent late-filing penalties and ensure accurate reporting of non-employee compensation. | Legal Compliance | Done | No
Phase 3 | Strategic Federal Credentialing & AI Compliance |  | Mar 2 - 6 | Full execution of the IRS Preparer Tax Identification Number (PTIN) application process. Managed document notarization and navigated a 'Foreign Status' pivot after initial denial to secure official federal acceptance. | Strategic Resilience & R&D Scalability: Overcame federal bureaucratic barriers to establish the legal framework for official representation. This provides the critical credentialing required to integrate and deploy proprietary in-house tax-prep software solutions, transforming compliance into a scalable technological asset. | Sr. Consulting / Software R&D | Done | Yes
Phase 3 | Strategic Federal Credentialing & AI Compliance |  | Mar 07 | Successfully completed the official IRS Paid Preparer Due Diligence Training (Program Number: CEQXT-T-01613-24-S). Earned 2 IRS-validated credits, formalizing technical expertise in federal tax preparation standards. | Risk Mitigation & Algorithmic Integrity: Ensures all future tax-prep software developed in-house adheres to strict federal Due Diligence requirements. Minimizes firm-wide liability by certifying that human oversight and automated workflows meet IRS ethical and legal standards. | Legal Compliance / Quality Assurance | Done | No
Phase 3 | Strategic Federal Credentialing & AI Compliance |  | Mar 9 | Completed CPE Course: IRS NOTICES EXPLAINED: HOW TO ASSIST YOUR CLIENTS AND RESPOND EFFECTIVELY (Program: HURS9-T-01894-25-O). Earned 1 IRS CE Credit. Mastery of official response protocols for federal tax notices. | AI Agent Training & Architecture: Technical mapping of IRS response workflows to be ingested by proprietary AI agents. This enables the automated generation of high-precision rebuttal documents and defense strategies for representation services, ensuring 100% alignment with IRS procedural requirements. | Software R&D / Automation | Done | No
Phase 3 | Omnichannel AI Integration & Lead Governance |  | Feb 14 - Ongoing | Official WhatsApp Business & Gemini AI Infrastructure Deployment: Successfully provisioned the official J&W WhatsApp Business line. Engineered a direct API bridge using a Google AI Studio Token and the WhatAuto middleware to link conversational flows with a Gemini Flash model. Developed and deployed the initial System Prompt Architecture to define the AI's persona, constraints, and business logic for preliminary engagement testing. | Interoperability & AI Governance: Establishing the foundational "Zero-Latency" lead capture system. By utilizing a proprietary System Prompt and API-level integration, we are securing a scalable, 24/7 automated response ecosystem that bypasses manual oversight while maintaining brand voice and data integrity. | AI Ecosystem Deployment | In Progress | Yes
Phase 3 | Proprietary BI Architecture & MEGA Dashboard Evolution |  | Mar 9 - Ongoing | Engineering the MEGA Dashboard as the firm’s primary Business Intelligence (BI) module. Developing a dynamic Admin-to-User Switching Toggle and custom data-abstraction layers to bypass Square’s native reporting limitations (lack of YoY comparisons and granular user-level segmentation). | Interoperability & Advanced RBAC: Solving a critical data security gap by filtering sensitive firm-wide revenue data. The system enables General Management (Nathaly) to pivot between global metrics and individual performance views, providing high-fidelity oversight while ensuring staff only access authorized, acoted data. | Software R&D / Data Governance | In Progress | Yes
Phase 3 | Automation & Workflow Engineering |  | Projected | Design and implementation of an automated notification system for the Payroll Department. The solution utilizes Google Sheets as a database and Apps Script as an orchestration engine to trigger customized Gmail reminder campaigns regarding service fee collections. | Operational Efficiency & Friction Mitigation: Automating pre-collection alerts to reduce inbound support tickets and client disputes. This technical workaround optimizes resource allocation by preventing human intervention in repetitive communication tasks and enhancing payment predictability. | RPA Workaround / Automation | Planning | No
Phase 3 | Evolution & Growth |  | Future | Marketing Bots Evolution: Advanced AI integration. | Strategic Roadmap: Scaling automated marketing through deep AI system integration. | Strategic Growth | Pending | No
Phase 3 | Evolution & Growth |  | Future | LedgerBot- Deployment for dynamic uploads and backup management. | Full Deployment: Transitioning the LedgerBot to app with Sessions and Default rules. | Checkout Efficiency | Pending | No
Phase 2 | IT Infrastructure & Disaster Recovery |  | Mar 10 | Comprehensive manual backup of ProSeries 25Data files. Execution of data redundancy protocols by migrating tax year datasets to independent, secure external storage sources. | Business Continuity & Risk Mitigation: Implementing a fail-safe data architecture to prevent information loss during Tax Season. This redundancy layer protects critical client tax records against system failures or software corruption, ensuring 100% data integrity and operational resilience. | Infrastructure / Risk Management | Done | No
Phase 2 | Financial Systems & API Infrastructure |  | Mar 11-12 | Responded to Co-Owner Christian Velasquez regarding Square daily sales report timing. Conducted a technical audit of Square’s settlement windows and bank clearing cycles. Identified that shifting the closing time from 8:00 PM to 11:00 PM triggers a 48-hour delay in fund availability. Evaluated Square's "Instant Transfer" 1.95% fee and rejected it. Implemented a hybrid configuration: optimized the cutoff to 12:00 AM (midnight) to capture a full 24-hour cycle (including late-night invoices) without additional settlement delays. Scheduled a rollback to the original 8:00 PM configuration for April 17 to restore 24-hour liquidity (T+1) post-peak season. | Data Governance & Cash Flow Optimization: Orchestrated a strategic workaround to balance operational visibility against liquidity needs. Engineered a hybrid scheduling model: prioritizing 24H data integrity during Tax Season and transitioning back to accelerated cash flow (Next-Day Refund) post-April 17. Mitigated unnecessary overhead while ensuring system resilience. | Financial Infrastructure / RPA Workaround | Done | No
Phase 2 | Financial Data Governance & Forensic Audit |  | Mar 13 - 14 | Massive Systemic Data Recovery & Audit: Initiated an emergency technical intervention following a report from Management containing critical email discrepancies. Identified that the source of the error was an external report with misaligned data that compromised profile integrity. To resolve this, I engineered a high-scale extraction of 5,932 total client records via Square API. Conducted a targeted forensic audit of 3,889 individual accounts to isolate a legacy "column-shift" error. After an exhaustive profile-by-profile verification to protect recent manual updates, I executed a bulk API restoration of 157 corrupted records, re-establishing the "Source of Truth" for the firm. | Advanced System Resilience: Mitigated the high-risk fallout of data corruption originated at the managerial report level. This operation required extensive technical man-hours to reconstruct data lineage without original CSV logs. It highlights that even minor misalignments in bulk data processing at high levels can trigger massive technical debt, necessitating senior-level intervention to ensure 100% billing accuracy and prevent legal-compliance failures. | Forensic Audit & API Restoration | Done | Yes